# Project Status Report

# Executive Overview

| Project name/ID: | ChitChat – COMP 2800 Group 4 |
| --- | --- |
| Project manager: | Deep Mandaliya |
| Date: | March 12, 2026 |
| Project summary: | ChitChat is a desktop real-time messaging application built in Java using Spring Boot, WebSocket (STOMP), and H2 database. It supports user authentication, private/group messaging, friend management, and message history persistence. |

# Overall Project Health

Status: On Track

Notes: Core features are complete. Sprint 3 work (profile page, read receipts) is in progress.

# Project Health Breakdown

| Element | Status | Owner | Notes |
| --- | --- | --- | --- |
| Backend / Server | Complete | Ayden Sendrea | Spring Boot + WebSocket server implemented |
| Database | Complete | Deep Mandaliya | 5 JPA entities, H2 file-based DB, BCrypt auth |
| Web Frontend | Complete | Asma Mohamed | Login + chat UI implemented |
| Desktop Client (JavaFX) | Complete | Stephen-Caleb Fallon | Connects to Spring Boot server |
| Profile Page | In Progress | Asma Mohamed | Bio/status fields designed |
| Read Receipts | In Progress | Ayden Sendrea | Planned for Sprint 3 |

# Milestone Review

| Milestone | Date |
| --- | --- |
| Sprint 1 – TCP prototype | January 21, 2026 |
| Sprint 2 – Spring Boot + Database + Messaging | February 15, 2026 |
| Sprint 3 – Profile, read receipts | March 20, 2026 (planned) |

# Risks

Known Issues:

Two branches (main vs master) not yet fully merged
  Action plan: Merging TCP socket classes into Spring Boot architecture this sprint.

MySQL on university server not directly accessible
  Action plan: Using H2 file-based DB as production fallback; data persists across restarts.

Potential Risks:

Server process may stop on reboot
  Action plan: Add startup script to auto-restart.

# Team Progress

Team's progress: Full-stack messaging app is functional with authentication, real-time chat, friend management, and message history.

Tasks completed:

TCP socket server with multithreaded client handling

Spring Boot WebSocket server with REST APIs

Database schema with 5 JPA entities and BCrypt authentication

Web frontend and JavaFX desktop client

Message history persistence across chat sessions

Friend management and group chat rooms

Tasks planned for next period:

User profile page (bio, status)

Read receipts ("Seen" indicator)

Final testing and documentation